## Sheet1
Job No. | Task | Assigned To | Comments | Deadline | Date Completed
1 | Add document of idea concepts to shared folder | Ruben Avis |  | 15.02.23 | 15.02.23
2 | Create team role template and add to shared folder | Referdinand Jr Balanquit |  | 15.02.23 | 15.02.23
3 | Research how to connect database in WampServer | Ivan Kvas | NULL | NULL | NULL
4 | Create folder for biscuit images | Sandra Miller |  | 24.02.23 | 24.02.23
5 | Create “team” description. (About us) | Ruben Avis |  | 28.02.23 | 16.03.23
6 | Create team role template and add to shared folder. | Ruben Avis |  | 5.03.23 | 5.03.23
7 | Write elevator pitch | Ruben Avis |  | 21.02.23 | 21.02.23
8 | Make word doc with guidance for formatting the information on Biscuits | Ruben Avis |  | 21.02.23 | 16.02.23
9 | Create 3 biscuit information logs each | Sandra Miller |  | 28.02.23
10 | Create 3 biscuit information logs each | Referdinand Jr Balanquit |  | 28.02.23
11 | Create 3 biscuit information logs each | Ruben Avis |  | 28.02.23 | 28.02.23
12 | Create 3 biscuit information logs each | Ivan Kvas |  | 28.02.23
NEW TASKS FROM 16.3.23
13 | Make Hero section HTML/CSS | Ruben Avis |  | 31.03.23
14 | Make Footer in HTML/CSS | Referdinand Jr Balanquit |  | 31.03.23
15 | Make Header in HTML/CSS | Ivan Kvas |  | 31.03.23
16 | Make Carousel interactivity in HTML/CSS | Sandra Miller |  | 31.03.23
17 | Get pictures of extra biscuits | Ruben Avis |  | 31.04.23