## Sheet1
Job No. | Task | Assigned To | Comments | Deadline | Date Completed
1 | Add document of idea concepts to shared folder | Ruben Avis |  | 15.02.23 | 15.02.23
2 | Create team role template and add to shared folder | Referdinand Jr Balanquit |  | 15.02.23 | 15.02.23
3 | Research how to connect database in WampServer | Ivan Kvas
4 | Create folder for biscuit images | Sandra Miller |  | 24.02.23 | 24.02.23
5 | Create “team” description. (About us) | Ruben Avis |  | 28.02.23
6 | Write HTML code to create background and basic header for website | Referdinand Jr Balanquit
7 | Write elevator pitch | Ruben Avis |  | 21.02.23 | 21.02.23
8 | Make word doc with guidance for formatting the information on Biscuits | Ruben Avis |  | 21.02.23 | 16.02.23
9 | Create 3 biscuit information logs each | Sandra Miller |  | 28.02.23
10 | Create 3 biscuit information logs each | Referdinand Jr Balanquit |  | 28.02.23
11 | Create 3 biscuit information logs each | Ruben Avis |  | 28.02.23 | 28.02.23
12 | Create 3 biscuit information logs each | Ivan Kvas |  | 28.02.23
13
14
Ruben Avis
1 | Add document of idea concepts to shared folder. | Ruben Avis
2 | Create team role template and add to shared folder. | Ruben Avis
3 |  | Referdinand Jr Balanquit
4 |  | Ruben Avis
5 |  | Ruben Avis
6 |  | Ruben Avis
7 |  | Ruben Avis
8 |  | Ruben Avis
9 |  | Ruben Avis
10 |  | Ruben Avis
11 |  | Ruben Avis
12 |  | Ruben Avis
13 |  | Ruben Avis